## Sheet1
Joint Inspection Checklist
|  | 2022-03-26 |  | 2022-07-25
Zawiyya Renovation Progress | Award Price | Amount Approved | % Approved | Amount Approved | % Approved | Remarks
Preliminary Works | 1000 | 1000 | 100% | 1000 | 100%
Wall and Ceiling Works
Remove Inconsistencies From the Walls and Ceiling | 500 | 450 | 90% | 500 | 100%
Skim Coat any inconsistencies on walls and ceiling | 1500 | 1305 | 87% | 1500 | 100%
Front Window Works | [5 empty] | To clean front window
Remove Existing Windows | 600 | 600 | 100% | 600 | 100%
Lay New Brick Works | 351 | 351 | 100% | 351 | 100%
Plaster and skim coat brick Work | 200 | 200 | 100% | 200 | 100%
Window Works
Supply and Install of Window | 1000 | 1000 | 100% | 1000 | 100%
Painting Works
Apply two coats finishing paint to the walls and ceiling | 2371 | 2252.45 | 95% | 2371 | 100%
Electrical Works
Install LED lighting | 1600 | 800 | 50% | 1600 | 100%
Install Ceiling Fans | 2100 | 1440 | 68.57% | 2100 | 100% | Add fans and to give the Warranties
Install Additional Socket Points | 840 |  | 0% | 0 | 0%
Exhaust fans for bathroom | 820 | 410 | 50% | 410 | 50% | Installed 1 only
Kitchen Works
Install concrete benchtop and sink | 1500 | 1125 | 75% | 1500 | 100% | To clean sink and benchtop
Tiling kitchen floor area | 1774 | 1774 | 100% | 1774 | 100%
Make good windows | 500 | 250 | 50% | 250 | 50% | Backcharged to Contract due to Contractor issue
Bathroom Works
Remove Old Windows | 200 | 0 | 0% | 0 | 0% | Old Windows not removed
Change Toilets | 1300 | 0 | 0% | 0 | 0% | Changed only pipings
Install New Wudhu Facility | 1200 | 1080 | 90% | 1200 | 100% | Clean Wudhu Facilities
Air Conditioning Works
Supply and install air conditioning copper pipe and PVC condensation piping | 860 | 430 | 50% | 860 | 100% | Conceal and Paint Piping
Installation of 2.5 HP Air Conditioner | 8000 | 5600 | 70% | 8000 | 100% | To give Warranty Card
Flooring Works
Remove Old Screeding | 600 | 300 | 50% | 600 | 100% | To Rectify 5 areas
Install new carpet tiles | 8680 | 6076 | 70% | 8680 | 100% | To Rectify 5 areas
Total Work Progress | 37496 | 26443.45 | 67.98% | 34496 | 81.82%
Attendees: Company | IC | Signature | Date | Signature | Date
Amirul Azmeer | 910302016343
Ahmad Firdaus